## Sheet1
Daily Activity Log
Project Name | InfoHub |  |  |  | Panaligan, Ma. Thrisha G
TASK | RESPONSIBLE | STATUS | DATES |  | Pelaez, Patricia Ann M.
|  |  | Start | End | Guillero, Lorenz Angelo
Creating Mockup System
- Login | Pelaez, Patricia Ann M. | Completed | June 19, 2023 | June 20, 2023 | Completed
- Dashboard | Panaligan, Ma. Thrisha G | Completed | June 19, 2023 | June 20, 2023 | In Progress
- Add Personnel | Panaligan, Ma. Thrisha G | Completed | June 19, 2023 | June 20, 2023 | Todo
- View Personnel | Guillero, Lorenz Angelo | Completed | June 19, 2023 | June 20, 2023 | Revision
- Add User | Panaligan, Ma. Thrisha G | Completed | June 19, 2023 | June 20, 2023
- View User | Guillero, Lorenz Angelo | Completed | June 19, 2023 | June 20, 2023
- Documents | Pelaez, Patricia Ann M. | Completed | June 19, 2023 | June 20, 2023
- View User Files | Pelaez, Patricia Ann M. | Completed | June 19, 2023 | June 20, 2023
- Document Requests | Pelaez, Patricia Ann M. | Completed | June 19, 2023 | June 20, 2023
Chapter 1 |  | Revision | June 19, 2023 | July 20, 2023
Chapter 2 |  | Revision | June 19, 2023 | July 20, 2023
Chapter 3 |  | Revision | June 19, 2023 | July 20, 2023
System |  | In Progress | June 19, 2023 | July 20, 2023
Database |  | In Progress | June 19, 2023 | July 20, 2023
System Architecture | Panaligan, Ma. Thrisha G | In Progress | June 19, 2023 | July 15, 2023
Data Flow | Pelaez, Patricia Ann M. | In Progress | June 19, 2023 | July 15, 2023
ERD | Guillero, Lorenz Angelo | In Progress | June 19, 2023 | July 15, 2023
System requirements |  | In Progress | June 19, 2023 | July 15, 2023
Documentation |  | Todo | June 19, 2023 | July 20, 2023